## Sheet1
Sprint Tracking Statistics |  |  |  |  | Priority | User Story | Success Criteria | Estimate | Owner | Status
Productive Hours = | 8 | Sprint Days = | 14 |  | High | As a player I want to build a structures easily. | Players can only build structures if player has enough money. | M | Aaron Healy | In Progress
|  | Scrum Team | %age of time on Project | Assigned Hours
|  | Aaron Healy | 100% | 8
|  | Leon Mulvaney | 100% | 8
|  | Alex Russell | 100% | 8
|  | Gavin Johnston | 100% | 8
|  | Conor Grant | 100% | 8 | High | As a player I want to upgrade my Troops so that I can have a stronger army. | Player can only upgrade if they have units or structures. Player can only upgrade if they have the required resources. Player can only upgrade if they are the required level. | M | Alex Russell | In Progress
[5 empty] | High | As a player, I want to be able to choose my payment method, may it be pay pal, a gift card or credit card. | Payment type can only be chosen if the user has added at least one item to their basket. | L | Leon Mulvaney | In Progress
[5 empty] | High | As a player I want to attack other planets so that I can go up in ranks. | Players can only attack planets that are of the same rank. | M | Conor Grant | In Progress
[5 empty] | High | As a player I want to defend my planet so that I can be victorious in battle. | Player can only defend their planet if they are being attacked | XL | Gavin Johnston | In Progress
[5 empty] | Medium | As a clan owner only I can declare war. | Clan can only go to war against another clan of similar power and size. | S | Aaron Healy | To be Started
[5 empty] | High | As a player I want to be able to compare my friend’s achievements with mine. | Player can only view their own and friend’s achievements. | XL | Alex Russell | To be Started
[5 empty] | Medium | As a player, I want to be able to choose a price to sell my item for | The player must have the item to choose the price to sell it at | M | Leon Mulvaney | To be Started
[5 empty] | High | As a player I want to be given the option to play a private multiplayer match so that I can potentially gain more resources. | Players can only battle other players if they are of the same rank | L | Gavin Johnston | To be Started
[5 empty] | High | As a player, I want to be able to describe myself on my profile so that other players can see information about me. | Players can only give a description of themselves if they are logged in. | XS | Conor Grant | To be Started